## Dashboard
GuestIQ — Sprint Analytics Dashboard
14-Week Prototype Project · Sprints 0–6 · Lead Researcher Dashboard
SECTION 1 — SPRINT VELOCITY
Sprint | Planned SP | Completed SP | Velocity | Goal Met? | Pipeline Runs | Pipeline Failures | Fix Cycles
Sprint 0 | 18 |  | — |  |  |  | —
Sprint 1 | 22 |  | — |  |  |  | —
Sprint 2 | 26 | 26 | 26 | Yes | 14 | 10 | 4
Sprint 3 | 35 |  | — |  |  |  | —
Sprint 4 | 28 |  | — |  |  |  | —
Sprint 5 | 18 |  | — |  |  |  | —
Sprint 6 | 12 |  | — |  |  |  | —
TOTALS / AVERAGE | 159 | 26 | 26 |  | 14 | 10 | 4
SECTION 2 — SPRINT GOAL ACHIEVEMENT RATE
Metric | Value | Notes
Sprints completed | 1 | Updates automatically as sprint data is entered
Goals achieved | 1 | Count of sprints where Goal Met = Yes
Goals missed | 0 | Count of sprints where Goal Met = No
Achievement rate | 100% | % of completed sprints where goal was fully met
Average velocity | 26 | Average story points completed per sprint
Total pipeline runs | 14 | Total GitHub Actions workflow runs across all sprints
Pipeline success rate | 28.57% | % of pipeline runs that deployed successfully
HOW TO USE THIS TRACKER
After each sprint | Go to the 'Sprint Log' sheet. Fill in the completed SP, goal achieved, pipeline runs, and pipeline failures for that sprint. This sheet auto-calculates everything.
Blue cells | Blue text = input cells you fill in manually. Black text = formulas that calculate automatically. Never edit formula cells.
Amber cells | Amber background = not yet filled in. Green background = data entered. Fill in as each sprint completes.
Burndown sheet | Go to 'Burndown' sheet after each working session and log story points remaining. The chart updates automatically.
Escaped defects | Go to 'Defects' sheet and log any bugs found in production (valkhot.github.io/guestiq) that were not caught during the sprint.

## Burndown
GuestIQ — Sprint Burndown Chart
Log story points remaining after each working session. Chart updates automatically.
Currently tracking: Sprint 2 (26 SP planned)
Day / Session | Ideal Remaining SP | Actual Remaining SP | % Complete | Notes
Day 1 — Project setup | 26 | 26 | 0% | S2-04 started
Day 2 | 24.1 | 26 | 0%
Day 3 — First deployment | 22.3 | 21 | 19.23% | S2-04, S2-05 complete
Day 4 | 20.4 | 21 | 19.23%
Day 5 — Sentry + PostHog | 18.6 | 16 | 38.46% | S2-02, S2-03 complete
Day 6 | 16.7 | 16 | 38.46%
Day 7 — Welcome screen | 14.9 | 9 | 65.38% | S2-06, S2-18 complete
Day 8 | 13 | 9 | 65.38%
Day 9 — Q0 + tense frame | 11.1 | 3 | 88.46% | S2-07, S2-08 complete
Day 10 | 9.3 | 3 | 88.46%
Day 11 — Module 1 | 7.4 | 0 | 100% | S2-09 complete
Day 12 | 5.6 | 0 | 100%
Day 13 — Modules 2-4 | 3.7 | 0 | 100% | S2-10 complete
Day 14 — Sprint close | 1.9 | 0 | 100% | Sprint 2 complete

## Sprint Log
GuestIQ — Detailed Sprint Log
Complete one row per story per sprint. Blue cells = enter data. Black cells = auto-calculated.
Sprint | Story ID & Name | Planned SP | Completed SP | Status | Days Taken | Blocked? | Notes
S2 | S2-04 React PWA project structure | 3 | 3 | Done | 3 | No | First green pipeline run #13
S2 | S2-05 Verify deployment to GitHub Pages | 2 | 2 | Done | 1 | No | 10 pipeline runs to green
S2 | S2-02 Sentry initialization | 3 | 3 | Done | 1 | No | Included in main.jsx init
S2 | S2-03 PostHog initialization | 2 | 2 | Done | 1 | No | app_loaded events confirmed
S2 | S2-06 Unified welcome screen | 5 | 5 | Done | 2 | No | 3 tier cards + hook text
S2 | S2-18 Privacy notice | 2 | 2 | Done | 1 | No | Combined with S2-06
S2 | S2-07 Q0 tense routing | 3 | 3 | Done | 2 | No | Session creation + Supabase write
S2 | S2-08 Tense frame engine | 3 | 3 | Done | 1 | No | Verified — no code change needed
S2 | S2-09 Module 1 questions Q1-Q9 | 5 | 5 | Done | 2 | No | intent_category + none_flags live
S2 | S2-10 Modules 2-4 Q10-Q38 | 5 | 5 | Done | 2 | No | scale_5 type added
Sprint 2 | 10 stories | 33 | 33 | Complete | 16 | 0 | Sprint 2 — all 10 stories delivered

## Defect Tracker
GuestIQ — Escaped Defect Tracker
Log bugs found in production (valkhot.github.io/guestiq) that were NOT caught during the sprint build and pipeline.
# | Sprint Found | Description | Severity | Found By | Fixed In Sprint | Resolution | Prevention Note
1 | S2 | autoFocus prop on text input — ESLint error | Low | Pipeline | S2 | Removed autoFocus attribute | ESLint jsx-a11y catches this — pipeline working correctly
2 | S2 | multi_select question type not registered in renderer | Medium | Lead Researcher | S2 | Added multi_select to QUESTION_RENDERERS map | Add new question types to renderer map when adding to questionnaire.js
3
4
5
DEFECT SUMMARY
Total escaped defects |  |  | -1
High severity |  |  | 0
Medium severity |  |  | 1
Low severity |  |  | 1
Resolved |  |  | -1

## Retrospective Log
GuestIQ — Sprint Retrospective Log
Record retrospective feedback and whether improvement actions were implemented in the next sprint.
Sprint | Category | Observation | Action Agreed | Implemented?
S2 | What Worked | Pipeline quality gate (ESLint + Prettier) caught errors before production | Continue using same pipeline structure in Sprint 3 | Yes
S2 | What Worked | Supabase data flowing from day one — real-time validation of data writes | Maintain practice of verifying Supabase after each story | Yes
S2 | What Worked | File-by-file delivery made changes trackable and reversible | Continue same delivery pattern | Yes
S2 | Improve | Pipeline fix cycles high (10 failures / 14 runs) — ESLint/Prettier issues took time | AI to run format check before providing files. Use PowerShell patch commands less. | —
S2 | Improve | Lead Researcher needs more explanation of what each file does and why | AI to provide plain-English explanation before each story build in Sprint 3 | —
S2 | Improve | File replacement process between AI outputs and local PC caused errors (wrong folder, missing dot prefix) | AI to provide clearer file destination instructions. Use direct PowerShell commands where possible. | —
S2 | Action Item | UX issues noted: auto-advance, Other layout, disabled button — formal refinement note raised | Implement two-step selection + Continue button in Sprint 3 question component rebuild | —