PROJECT CHARTER

GuestIQ — Hotel Guest Expectations Research Application

VERSION 2.1 — POST-METHODOLOGY UPDATE

| Document Version | 2.1 — Updated to reflect methodology decisions from Sprint 0 planning discussion |
| --- | --- |
| Previous Version | 1.0 — Initial Release (approved by Lead Researcher) |
| Document Status | APPROVED v1.0 and v2.0 — v2.1 PENDING RE-APPROVAL |
| Application Name | GuestIQ |
| Project Name | GuestIQ — Hotel Guest Expectations Research Application — Internal Pilot |
| Project Sponsor | [Hotel Management — To Be Completed] |
| Lead Researcher | [Name — To Be Completed] |
| Developer | Claude (Anthropic AI) — AI Development Partner |
| v1.0 Approval Date | [Date of v1.0 Approval] |
| v2.0 Date Prepared | [Insert Date] |
| v2.0 Approval Date | [Insert Date Upon Re-Approval] |
| Document Location | 00-Sprint-0 / Approved / Project-Charter-v2.0.docx |

★  VERSION 2.0 CHANGE SUMMARY — 6 sections updated following post-approval planning decisions

| Ver. | Section | Change Made |
| --- | --- | --- |
| v2.0 | Cover & Metadata | Application name confirmed as GuestIQ. Version updated to 2.0. |
| v2.0 | Section 1 — Purpose | Added GuestIQ name. Added production-readiness as founding design principle. Added content management strategy (Strangler Fig Pattern). Added observability strategy (Sentry + PostHog). |
| v2.0 | Section 2 — Objectives | Added production-readiness objective. Added content management objective. Added observability objective. Added questionnaire editability objective. |
| v2.0 | Section 3 — Scope In | Added 14 new in-scope items covering full confirmed technology stack, observability tools, content management phases, and production-readiness architecture. |
| v2.0 | Section 3 — Scope Out | Added 4 new out-of-scope items. Clarified Phase 2 items that were previously undefined. Added visual admin CMS as explicit Phase 2 item. |
| v2.0 | Section 7 — Budget | Added PostHog and Sentry to confirmed $0 budget. Added Node.js as free tool. Added Radix UI, ESLint, Prettier, Playwright as free tools. Total remains $0. |
| v2.0 | Section 8 — Risks | Added 2 new risks: content configuration file corruption and Supabase project accidental deletion. Updated mitigation strategies for both. |
| v2.0 | Section 11 — Success | Added content management and observability to success criteria. Added production-readiness validation criterion. |
| v2.0 | Section 12 — Approval | Re-approval required for all signatories following material scope additions. |
| v2.1 | Cover & Metadata | Version updated to 2.1. Document status updated. |
| v2.1 | Section 13 — NEW | Delivery Methodology section added: six-framework hybrid stack, JTBD statements (3 actors), North Star Metric, Scrum Master function, Epic hierarchy, BDD-TDD Option A, PLG Phase 1 mechanics. |
| v2.1 | Section 8 — Risks | Risk count corrected from 10 to 12 — reflecting R-11 and R-12 added in Risk Register v1.1. |
| v2.1 | Section 12 — Approval | Re-approval required for v2.1. All changes are additive. |

ℹ NOTE:  Version 2.0 reflects all decisions made during the planning phase following v1.0 approval. All changes are additive — no previously approved content has been removed or contradicted. The project scope has been extended and clarified, not reduced. Re-approval by all signatories is required before Sprint 1 begins.

# 1. PROJECT PURPOSE

★ UPDATED v2.0:  Section updated in v2.0: Application name GuestIQ added. Production-readiness, content management, and observability added as founding principles.

The hotel industry operates with a persistent and commercially consequential blind spot: systematic, reliable data on why guests choose a hotel for a specific stay purpose and what they genuinely expect from that experience. Most guest satisfaction tools measure how a stay felt after the fact — but without capturing what the guest needed, expected, and used as their evaluative reference point, that satisfaction data cannot be translated into operational decisions with confidence.

This project develops, deploys, and validates GuestIQ — a gamified Progressive Web Application (PWA) that captures hotel guest expectation data from hotel front desk professionals in an internal pilot setting. GuestIQ delivers a 79-question research instrument across three adaptive tiers (Amateur, Professional, Expert) using gamification mechanics, episodic question delivery, and real-time results visualization to achieve completion rates that standard survey tools cannot match in a professional hospitality setting.

GuestIQ is designed from its first line of code as an evolutionary prototype — a system built to production-grade standards that grows into the production system without a rebuild. This founding design principle governs every architectural decision: authentication infrastructure is built in bypass mode and activated in Phase 2; the database schema is versioned and migration-managed from Sprint 1; the questionnaire content is separated from application code and made editable without developer involvement; observability tools (Sentry for error tracking, PostHog for product analytics) are instrumented from day one so performance and user behavior data is available immediately when the pilot begins.

The immediate output is a validated, engaging, zero-IT-investment research tool deployed on the front desk team's existing Windows PCs, accessible via a single URL (guestiq.github.io), requiring no login, and generating real-time analytics through a hidden management dashboard (SHIFT+CTRL+A). The strategic output is a methodology and platform that can be extended to guest-facing deployment, multi-property benchmarking, and ongoing operational intelligence at scale.

# 2. PROJECT OBJECTIVES

★ UPDATED v2.0:  Section updated in v2.0: Three new primary objectives added covering production-readiness, content management, and observability. Three new secondary objectives added.

## 2.1 Primary Objectives

- Build and deploy GuestIQ — a fully functional Progressive Web App delivering the Hotel Guest Expectations questionnaire across three adaptive tiers — to front desk team members at a single property within 14 weeks.

- Achieve a pilot participation rate of at least 70% of the target front desk team (7 of 10 members) starting the questionnaire within the pilot window.

- Achieve a pilot completion rate of at least 60% of participating team members completing their selected tier within the pilot window.

- Demonstrate that the gamified episodic delivery format generates higher engagement than a standard survey format for a hospitality professional audience.

- Collect a statistically preliminary but operationally meaningful dataset from the front desk pilot sufficient to generate at least 3 actionable operational insights for hotel management.

- Produce a complete set of 34 project artifacts across all 6 sprints as specified in the Master Development Timeline.

- Build GuestIQ as an evolutionary prototype — designed to production-grade standards from Sprint 1 so it grows into the production system without a rebuild. All seven production-readiness gaps (authentication, environment configuration, feature flags, error logging, database migrations, API versioning, dashboard caching) addressed in the prototype architecture.

- Implement a content management strategy that allows questionnaire questions, answer options, modules, tiers, and branching logic to be edited without modifying application code — using hardcoded content in Phase 1a, JSON configuration files in Phase 1b, and a visual admin interface in Phase 2.

- Instrument GuestIQ with Sentry (error tracking and performance monitoring) and PostHog (product analytics and session replay) from Sprint 2 day one — so behavioral data and error data are available from the first pilot session.

- Validate the technical architecture — GitHub Pages hosting, Supabase data storage, browser local storage session resume with disambiguation screen, SHIFT+CTRL+A management overlay — as stable, zero-IT, and production-ready for Phase 2 scaling.

## 2.2 Secondary Objectives

- Assess the front desk team's perception of the questionnaire experience as engaging, relevant, and professionally appropriate through User Acceptance Testing feedback.

- Identify which of the 12 guest intent taxonomy categories the front desk team perceives as most prevalent at this property — and compare against available PMS booking data as a validity check.

- Establish baseline velocity data (story points completed per sprint) to inform Phase 2 project planning.

- Verify that the Strangler Fig content migration — from hardcoded questionnaire.js to JSON configuration files — can be executed without any visible change to the respondent experience.

- Generate a complete PostHog funnel analysis showing drop-off rates at each episode across all three tiers — the primary instrument for optimizing the questionnaire experience in Phase 2.

- Document all lessons learned across the 6 sprints in a format directly usable for Phase 2 Sprint 0 planning.

- Produce a Phase 2 recommendations document covering multi-property expansion, authentication implementation, language support, visual admin CMS, and instrument refinements based on pilot findings.

## 2.3 What This Project Is NOT Attempting

- Psychometric validation of the guest intent taxonomy — this requires a larger guest-facing sample and is a Phase 2 academic objective.

- Deployment to actual hotel guests — this project is staff-facing only in Phase 1.

- Building the visual admin CMS — the content editing interface is a Phase 2 sprint, not a Phase 1 deliverable.

- Integration with the property management system (PMS) or any existing hotel technology infrastructure.

- Multi-language translation — architecture is i18n-ready but translation is Phase 2.

- Revenue management optimization — the instrument generates data that informs revenue strategy but does not directly interface with revenue management systems.

# 3. PROJECT SCOPE

★ UPDATED v2.0:  Section updated in v2.0: 14 new in-scope items added. 4 new out-of-scope items added. Content management phases clarified.

## 3.1 In Scope — Phase 1 Prototype

Application Experience

✓ IN SCOPE:  GuestIQ Progressive Web App — complete respondent experience from welcome screen to results screen

✓ IN SCOPE:  Three-tier adaptive instrument — Amateur (5 min, 8 questions), Professional (8 min, 18 questions), Expert (16 min, 79 questions)

✓ IN SCOPE:  Welcome experience — three-beat hook sequence, tier selection with Amateur/Professional/Expert identity labels, expert credentials warm-up

✓ IN SCOPE:  Routing gate — dual-tense (retrospective/anticipatory) assignment applied throughout all 7 modules

✓ IN SCOPE:  All 79 refined questions across 7 modules with correct tier routing, branching logic, and 'None of these fit my situation' escape valve

✓ IN SCOPE:  Module 5 branching — all 12 intent category sub-sections with secondary purpose routing

✓ IN SCOPE:  Gamification layer — progress bar, episode map with 7 named episodes, 9 SVG achievement badges, curiosity hooks, tier upgrade prompts, streak mechanic, completion celebration

✓ IN SCOPE:  Real-time personal results and anonymized aggregate comparison on completion screen

✓ IN SCOPE:  Session resume via browser local storage with disambiguation screen for shared PC handoffs

✓ IN SCOPE:  Supabase downtime contingency — static 'temporarily unavailable' screen

Content Management — Strangler Fig Pattern

✓ IN SCOPE:  Phase 1a — All questionnaire content hardcoded in questionnaire.js — single centralized data file, components accept content as properties and never contain content directly

✓ IN SCOPE:  Phase 1b — Content extracted from questionnaire.js to six JSON configuration files (questions.json, episodes.json, tiers.json, ui-copy.json, branching.json, taxonomy.json) after Sprint 3 testing — executed as Strangler Fig migration with no visible change to respondent experience

✓ IN SCOPE:  Configuration validator — verifies JSON file integrity on application load, fails loudly on malformed files before any respondent encounters an error

Management and Analytics

✓ IN SCOPE:  Management dashboard — SHIFT+CTRL+A overlay with 9 analytics panels, CSV export, PDF summary report

✓ IN SCOPE:  Sentry — JavaScript error tracking, performance monitoring, Core Web Vitals from real user devices

✓ IN SCOPE:  PostHog — product analytics with 27 named events, funnel analysis, session replay, IP anonymization enabled

Infrastructure and Architecture

✓ IN SCOPE:  GitHub Pages hosting — free, zero-maintenance, URL: guestiq.github.io?property=PROP001

✓ IN SCOPE:  GitHub Actions CI/CD — automatic deployment on every code push

✓ IN SCOPE:  Supabase data storage — 4-table schema implemented via Supabase Migrations for version control

✓ IN SCOPE:  Supabase Auth — configured in bypass mode in prototype, switches to active authentication via feature flag in Phase 2

✓ IN SCOPE:  Feature flag system — environment configuration file controls prototype/production feature switching

✓ IN SCOPE:  Service layer architecture — all Supabase calls through dedicated service functions, never directly from components

✓ IN SCOPE:  ESLint + Prettier — code quality and formatting configured in Sprint 1 before any code is written

✓ IN SCOPE:  Radix UI — headless accessible component library as interactive component foundation

✓ IN SCOPE:  Playwright — visual regression testing configured in Sprint 4

✓ IN SCOPE:  Offline response queue — Supabase unreachability detection, local queue, automatic retry

✓ IN SCOPE:  Single property pilot — up to 10 front desk team members

✓ IN SCOPE:  Multi-property architecture foundations — property_id field in all database records and PostHog events, unused in prototype

✓ IN SCOPE:  i18n-ready architecture — all text in external files via i18next, English only implemented

✓ IN SCOPE:  WCAG 2.1 AA accessibility compliance

✓ IN SCOPE:  Cross-browser compatibility — Microsoft Edge and Google Chrome on Windows

✓ IN SCOPE:  Mobile browser functionality as secondary priority

✓ IN SCOPE:  34 project artifacts across all 6 sprints

## 3.2 Out of Scope — Phase 1 Prototype

✗ OUT OF SCOPE:  Individual login credentials or account management — prototype is open access, authentication in bypass mode only

✗ OUT OF SCOPE:  Single Sign-On (SSO) or Windows Active Directory integration

✗ OUT OF SCOPE:  Visual admin CMS — the Phase 2 content editing interface at /admin route with form-based question editing, drag-and-drop reordering, draft/publish workflow

✗ OUT OF SCOPE:  Multi-property features — cross-property comparison, central management console, property-specific branding (property_id field exists in all records but is unused)

✗ OUT OF SCOPE:  Any language other than English — i18n architecture ready, translation deferred to Phase 2

✗ OUT OF SCOPE:  Guest-facing deployment — staff only in Phase 1

✗ OUT OF SCOPE:  Native iOS or Android app — PWA only

✗ OUT OF SCOPE:  Push notifications or offline mode (offline response queue is included — full offline mode is not)

✗ OUT OF SCOPE:  PMS integration or any existing hotel system integration

✗ OUT OF SCOPE:  Statistical significance testing, regression analysis, or psychometric validation

✗ OUT OF SCOPE:  Longitudinal respondent tracking across multiple sessions

✗ OUT OF SCOPE:  Kiosk mode, QR code generation, or lobby deployment

✗ OUT OF SCOPE:  Post-stay email automation integration

✗ OUT OF SCOPE:  Dashboard materialized views and caching — Phase 2 performance optimization when response volume warrants it

## 3.3 Scope Change Process

Any request to add items currently listed as Out of Scope requires a formal Scope Change Request submitted in writing, reviewed by the Project Sponsor and Lead Researcher, assessed for timeline and cost impact by the Developer, and approved by all three parties before any work begins. Scope changes after Sprint 2 has begun carry a high risk of timeline extension and must be carefully evaluated against the 14-week completion commitment.

# 4. SUCCESS CRITERIA

The project is considered a success when it meets all Minimum Threshold criteria below. Stretch Targets represent outstanding outcomes. All criteria are assessed at the Sprint 6 debrief meeting.

| Success Criterion | Minimum Threshold | Stretch Target | Measurement Method |
| --- | --- | --- | --- |
| Prototype delivered within 14-week timeline | Yes — live by Week 12 | Live by Week 10 | Master Development Timeline completion date |
| All 34 artifacts produced and approved | 34 of 34 complete | 34 of 34 with zero rework | Artifact registry Sprint 6 |
| Pilot participation rate | 70% starts (7/10) | 90% starts (9/10) | Supabase session count |
| Pilot completion rate | 60% complete selected tier | 80% completion rate | is_complete flag in sessions |
| Average tier selected | 50% select Professional+ | 20% select Expert | Tier field distribution |
| Data completeness — Module 1 | 80% include full Module 1 | 95% include full Module 1 | Q1–Q9 per session |
| None of these escape rate | Under 15% per question avg | Under 8% per question | none_flags table |
| Technical stability | Zero critical bugs in pilot | Zero medium bugs | Bug log Sprints 5–6 |
| Operational insights | 3 actionable insights | 5+ insights at debrief | Debrief report |
| Management dashboard access | 1+ dashboard sessions | 3+ with export | Dashboard access log |
| UAT satisfaction | All UAT participants 3+/5 | Average 4+/5 | UAT feedback form |
| Zero IT involvement | Yes — no IT contact needed | — | Sprint 2 deployment log |
| Production-readiness validated | All 7 architecture gaps confirmed working | — | Sprint 4 architecture review |
| Content management validated | Phase 1b JSON migration complete with no visible change | — | Sprint 3 extraction task |
| Observability confirmed | Sentry errors + PostHog events flowing from first pilot session | — | Sentry + PostHog dashboards |
| Branching logic verified | All 84 routing paths pass test matrix | — | Sprint 3 test matrix results |

# 5. STAKEHOLDERS

The following stakeholders have a direct interest in or influence over this project. This register is updated at the start of each sprint if new stakeholders are identified.

| Stakeholder / Role | Interest | Influence | Communication | Notes |
| --- | --- | --- | --- | --- |
| Hotel Management / Project Sponsor | Operational insights, ROI, pilot success, Phase 2 decision | High — final decision authority | Sprint reviews, Debrief report, Dashboard access | Approves Charter. Makes Phase 2 continuation decision. |
| Lead Researcher | Instrument quality, data validity, publishable findings, Phase 2 | High — drives all research decisions | Daily AI collaboration, all artifact reviews, pilot facilitation | Approves all 34 artifacts. Primary human team member. |
| Front Desk Team (10 members) | Engaging experience, time respected, seeing input matter | Medium — participation determines data quality | MS Teams launch message, mid-pilot check-in, results screen | Primary research subjects. UAT participants drawn from this group. |
| Claude / AI Developer | Producing code and artifacts to specification within sprint schedule | High — produces all AI deliverables | In-conversation delivery of all outputs | Bound by approved artifacts. No unilateral scope changes. |
| Property Owner / Investor | Research ROI, guest satisfaction improvement, competitive intel | Low in Phase 1 | Debrief report summary only | Not involved in day-to-day project decisions. |
| Future Research Collaborators | Instrument validity, publishable data, citation potential | Low in Phase 1 | Publication of findings post-pilot | Engaged in Phase 2 if academic publication pursued. |

## 5.1 Stakeholder Communication Plan

| Sprint Review (end of each sprint) | Lead Researcher reviews sprint output. Hotel Management briefed on progress. |
| --- | --- |
| Sprint Gate Sign-Off | Lead Researcher confirms all gate conditions met before next sprint begins. |
| Mid-Pilot Check-In (Day 5 of pilot) | Lead Researcher speaks informally with front desk team. Feedback collected. |
| Pilot Debrief Meeting | 45-minute meeting with Hotel Management. Findings presented. Phase 2 decision made. |
| Artifact Delivery | All AI-produced artifacts delivered in this conversation. Human review within 48 hours. |
| Bug Reports (during pilot) | Logged via MS Teams to Lead Researcher. Critical bugs addressed within 24 hours. |
| Sentry Alerts | Automatic error alerts to Lead Researcher email. Configured in Sprint 2. |
| PostHog Weekly Digest | Optional weekly product analytics digest email. Configured in Sprint 2. |

# 6. HIGH-LEVEL TIMELINE

The project is organized into 6 two-week sprints preceded by a Pre-Sprint setup phase. The Pre-Sprint now includes 9 setup tasks including PostHog, Sentry, and Node.js setup in addition to GitHub and Supabase.

| Sprint | Weeks | Focus | Key Deliverables | Hours |
| --- | --- | --- | --- | --- |
| Pre-Sprint | Before Wk 1 | Setup & Accounts | GitHub, Supabase, PostHog, Sentry accounts. Node.js install. Project folders. 9 tasks total. | 2.5 hours |
| Sprint 0 | Weeks 1–2 | Foundation & Governance | 10 artifacts: Project Charter, SRS, Product Backlog, Use Cases, Risk Register, Test Plan, plus 4 new architecture artifacts. | 8–9 hours |
| Sprint 1 | Weeks 3–4 | Architecture & Design | 9 artifacts including Branching Logic Spec + 84-path test matrix, questionnaire.js data structure, SVG badge specs, Visual Design System. | 7–8 hours |
| Sprint 2 | Weeks 5–6 | Core Application Build | Working URL live. Modules 1–4 functional. Sentry + PostHog live. Session resume + disambiguation. Data in Supabase. | 8–10 hours |
| Sprint 3 | Weeks 7–8 | Full Questionnaire + Gamification | All 79 questions. All 12 Module 5 branches. Full gamification. Results screen. Phase 1b JSON extraction. | 8–10 hours |
| Sprint 4 | Weeks 9–10 | Dashboard + Polish + QA | SHIFT+CTRL+A complete. Playwright visual regression. Downtime screen. Full QA. UAT Script ready. | 8–10 hours |
| Sprint 5 | Weeks 11–12 | UAT + Pilot Launch | UAT with 2–3 team members. Critical fixes. Pilot launched via MS Teams. | 8–10 hours |
| Sprint 6 | Weeks 13–14 | Pilot + Debrief | Monitoring. Weekly CSV backup to OneDrive. Final export. Debrief report. Phase 2 plan. | 6–8 hours |

## 6.1 Key Milestones

| Pre-Sprint Complete | 9 accounts and tools active. GitHub, Supabase, PostHog, Sentry configured. Node.js installed. |
| --- | --- |
| Sprint 0 Gate | All 10 governance documents approved. Branching test matrix complete. Visual design locked. |
| Sprint 1 Gate | Branching Logic Spec + 84-path matrix approved. All 9 architecture documents approved. |
| Sprint 2 Gate — First Working URL | App live at guestiq.github.io. Sentry + PostHog receiving data. Modules 1–4 functional. |
| Sprint 3 Gate — Complete Experience | All 79 questions live. Phase 1b JSON extraction complete. Full gamification live. |
| Sprint 4 Gate — Prototype Complete | Dashboard complete. Playwright passing. Full QA passed. UAT Script approved. |
| Sprint 5 Milestone — Pilot Launch | MS Teams message sent. First PostHog events and Sentry session recorded. |
| Sprint 6 Gate — Project Complete | Pilot closed. Debrief delivered. Phase 2 decision made. 34 artifacts filed. |

# 7. BUDGET

★ UPDATED v2.0:  Section updated in v2.0: PostHog, Sentry, Radix UI, ESLint, Prettier, Playwright, Node.js all confirmed as free. Total direct cost remains $0.

The Phase 1 prototype is designed to be produced at zero direct monetary cost. The complete confirmed technology stack operates within free-tier limits throughout the prototype duration.

| GitHub Pages (app hosting) | Free — unlimited for public and private repositories |
| --- | --- |
| GitHub Actions (CI/CD) | Free — 2,000 minutes per month on free tier. Prototype deployments use approximately 20 minutes total. |
| Supabase (database + auth) | Free tier — 500MB storage, 50,000 monthly active users. Far exceeds prototype needs. |
| PostHog (product analytics) | Free tier — 1 million events per month. Prototype generates approximately 5,000 events total. |
| Sentry (error tracking) | Free tier — 5,000 errors per month. Prototype unlikely to generate more than 100. |
| React 18 + Vite | Free — open source |
| Radix UI (headless components) | Free — open source. Saves approximately 10 hours of accessible component build time. |
| Tailwind CSS | Free — open source |
| Framer Motion | Free — open source |
| Recharts | Free — open source |
| i18next | Free — open source |
| ESLint + Prettier | Free — open source |
| Playwright (visual regression) | Free — open source |
| Node.js | Free — open source. Required for local development environment. |
| Custom domain (optional) | ~$12/year if guestiq.com or similar preferred. Not required — guestiq.github.io works for prototype. |
| AI Development (Claude) | Included in existing Claude subscription |
| Your time investment | 53–67 hours across 14 weeks — real opportunity cost, zero monetary cost |
| TOTAL DIRECT COST | $0 for prototype (optional $12/year for custom domain) |

ℹ NOTE:  Phase 2 costs will differ if Supabase Pro tier is needed for higher volume, professional translation services are engaged, or the visual admin CMS requires additional infrastructure. A Phase 2 budget estimate is produced as part of the Sprint 6 Phase 2 Recommendations Document.

# 8. KEY PROJECT RISKS

★ UPDATED v2.0:  Section updated in v2.0: 2 new risks added — content configuration file corruption and Supabase project accidental deletion. All original risks retained.

The following risks are assessed for probability and impact with mitigation strategies defined. This register is updated at the start of every sprint. A full Risk Register is maintained as a separate living document.

| Risk | Prob. | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Decision latency — artifact reviews take longer than 48 hours, delaying sprint starts | High | High | Lead Researcher blocks dedicated review time at sprint start. 48-hour review turnaround is a project commitment. |
| Branching logic errors — routing errors create bugs requiring significant Sprint 3 rework | Medium | High | 84-path branching test matrix produced in Sprint 1 and reviewed before Sprint 2. Sprint 1 gate cannot pass without this. |
| Low front desk pilot participation — fewer than 70% of team start the questionnaire | Medium | High | Identity-based tier labels motivate participation. Manager encourages team. Follow-up Teams message on Day 5 if below target. |
| Browser incompatibility — front desk PCs use unsupported browser | Low | High | Verified on actual front desk PCs in Sprint 2 testing. Edge and Chrome are pre-installed on Windows 10/11. |
| Content configuration file corruption — malformed JSON breaks the application on load | Medium | Medium | Configuration validator runs on application load and fails with a clear error message before any respondent encounters it. JSON files are version-controlled in Git. |
| Supabase project accidental deletion — all pilot data lost | Low | High | Weekly CSV export to OneDrive during Sprint 6 pilot. Supabase project protected by email verification for deletion. Addressed in Sprint 6 monitoring checklist. |
| Supabase connectivity issue — hotel internet blocks API calls | Low | Medium | Offline queue handles brief outages. Downtime screen handles extended outages. Response data never lost. |
| Scope creep — new features requested during build sprints | Medium | Medium | All scope changes require formal change request and approval. This Charter defines boundaries. Changes after Sprint 2 require timeline reassessment. |
| Gamification disengagement — mechanics feel patronizing to professional audience | Low | Medium | UAT in Sprint 5 specifically tests this. Identity-based tier labels establish professional framing before gamification appears. |
| PostHog or Sentry data privacy concern | Low | Low | Both configured with IP anonymization enabled. No PII collected. Privacy notice displayed on welcome screen. |

# 9. CONSTRAINTS AND ASSUMPTIONS

## 9.1 Constraints

- The application must require zero IT department involvement to deploy and operate.

- The application must run on existing front desk PC hardware without any software installation by hotel staff.

- The prototype must be delivered within 14 weeks from project start.

- All hosting and infrastructure must operate within free-tier service limits.

- The questionnaire content — 79 questions across 7 modules — is fixed as per the Refined Questionnaire document for Phase 1. Questions may be refined between tiers but the Expert tier content is locked for the prototype.

- The application is English-language only in Phase 1. No translation work is performed.

- The application handles a maximum of approximately 50 concurrent users in the prototype — well within all free-tier limits.

- All components must be built to accept content as external properties — never containing hardcoded content directly. This architectural discipline is required for the Phase 1b Strangler Fig migration to succeed.

## 9.2 Assumptions

- Front desk PCs run Windows 10 or Windows 11 with Microsoft Edge or Google Chrome available.

- Front desk PCs have standard hotel broadband internet allowing outbound HTTPS connections to GitHub, Supabase, PostHog, and Sentry.

- The Lead Researcher has a PC or laptop with Node.js installed for local development review and testing.

- Hotel management supports the pilot and encourages team participation without mandating it.

- The front desk team has at least 5 minutes of lull time available during a typical shift.

- MS Teams or corporate email is available for sending the pilot launch message and receiving bug reports from team members during the pilot.

- GitHub, Supabase, PostHog, and Sentry free-tier services remain available throughout the 14-week project duration.

- The Supabase project is not accidentally deleted during the pilot — weekly CSV backup to OneDrive is the mitigation.

# 10. CONFIRMED TECHNOLOGY STACK

All technology decisions are confirmed and locked. Every tool operates within its free tier for the full prototype duration. No tool requires installation on hotel hardware.

| Technology | Layer | Purpose | Cost | Confirmed |
| --- | --- | --- | --- | --- |
| React 18 + Vite | Frontend | Application framework and build tooling | Free | ✓ Locked |
| Radix UI | Frontend | Headless accessible component library | Free | ✓ Locked |
| Tailwind CSS | Frontend | Utility-first CSS — GuestIQ design tokens | Free | ✓ Locked |
| Framer Motion | Frontend | Animation — progress bar, badges, transitions | Free | ✓ Locked |
| Recharts | Frontend | Charts — results screen and dashboard | Free | ✓ Locked |
| i18next | Frontend | i18n architecture — English only in prototype | Free | ✓ Locked |
| Vite PWA Plugin | Frontend | PWA config + session persistence | Free | ✓ Locked |
| ESLint + Prettier | Developer tools | Code quality + consistent formatting | Free | ✓ Locked |
| Supabase | Backend | Database, auth, real-time, migrations | Free tier | ✓ Locked |
| Supabase Auth | Backend | Bypass mode in prototype — active in Phase 2 | Free tier | ✓ Locked |
| Supabase Migrations | Backend | Schema versioning from Sprint 1 | Free | ✓ Locked |
| GitHub Pages | Hosting | App hosting at guestiq.github.io | Free | ✓ Locked |
| GitHub Actions | CI/CD | Auto-deploy on code push | Free | ✓ Locked |
| Sentry | Observability | Error tracking + performance monitoring | Free tier | ✓ Locked |
| PostHog | Observability | Product analytics + session replay | Free tier | ✓ Locked |
| Playwright | Testing | Visual regression screenshots | Free | ✓ Locked |
| Node.js | Development | Local development environment on researcher PC | Free | ✓ Locked |

# 11. DEFINITION OF PROJECT SUCCESS

The project is formally declared successful at the Sprint 6 debrief meeting when all of the following conditions are confirmed:

| 1 | The prototype is live and accessible at guestiq.github.io. |
| --- | --- |
| 2 | At least 7 of 10 front desk team members have started the questionnaire. |
| 3 | At least 5 complete session records exist in Supabase. |
| 4 | The management dashboard (SHIFT+CTRL+A) returns data correctly. |
| 5 | At least one CSV export and one PDF report have been successfully generated. |
| 6 | At least 3 actionable operational insights have been identified from pilot data. |
| 7 | All 34 project artifacts are filed in their respective sprint Approved folders. |
| 8 | Sentry has recorded at least one session with no critical unresolved errors. |
| 9 | PostHog shows a complete funnel from app_loaded through session_completed for at least 5 sessions. |
| 10 | The Phase 1b JSON content migration has been completed with no visible change to respondent experience. |
| 11 | The debrief meeting has been conducted with hotel management. |
| 12 | A Phase 2 continuation decision has been made (yes, no, or deferred). |
| 13 | The project retrospective is complete and lessons learned are documented. |

# 13. DELIVERY METHODOLOGY

★ UPDATED v2.0:  ADDED v2.1: This section documents the hybrid delivery framework agreed during Sprint 0 planning. It is the anchor for all v1.1 updates to Sprint 0 artifacts. All content is additive — nothing in previous sections is changed.

13.1 Hybrid Framework Stack

GuestIQ is developed using six active frameworks simultaneously. Each occupies a distinct layer of the project — they do not compete, they complement.

| Framework | Role in GuestIQ |
| --- | --- |
| F-01 Use Case 3.0 (Jacobson / Cockburn, Dec 2024) | Requirements and traceability. Use Case Storytelling practice. Use Cases = Epics. Slices = Features. Work Items = Stories. |
| F-02 Scrum | Sprint delivery. 2-week cadence. Backlog. Velocity. DoD/DoR. Sprint gates. Retrospectives. Adapted for one-person team. |
| F-03 PRINCE2-lite Governance | Formal project initiation artifacts: Charter, RACI, Risk Register, Stakeholder Register. Sequential gate-based approval. |
| F-04 Academic Research Methodology | Instrument validity and reliability. Dual-tense design. 12-category taxonomy coding. Research data quality (NFR-043/044/045). |
| F-05 Behaviour-Driven TDD — Option A | Three instruments: 84-path branching test matrix (Sprint 1), Playwright visual regression baseline (Sprint 4), Data integrity verification protocol (Sprint 2). Test specification always precedes implementation. |
| F-06 Product-Led Growth — Phase 1 | Engagement loop: Trigger → Episode → Reward → Expand. NSM tracking via PostHog. Time-to-value per tier. Aha moment: results screen aggregate comparison. |

13.2 Jobs-to-Be-Done — Three Actor Statements

GuestIQ serves three distinct actors, each hiring the product for a different job. These statements are the reference for all product decisions.

Actor 1 — Hotel Management Hires GuestIQ to translate the front desk team's collective knowledge of guest behaviour into structured, segmented data — so that operational decisions about service design, staffing, and positioning are made with evidence rather than accumulated assumption.

Actor 2 — Lead Researcher Hires GuestIQ to prove that a gamified, episodic digital instrument can collect research-grade guest expectation data from front desk professionals at higher completion rates than conventional survey methods — producing a dataset that is simultaneously publishable and operationally useful.

Actor 3 — Front Desk Team Hires GuestIQ to give their professional expertise about guest behaviour a form — converting what they know from thousands of interactions into structured data that is visible, valued, and consequential beyond the front desk.

ℹ  Full JTBD analysis — including barriers, success signals, switching events, and product decisions per actor — is documented in the JTBD Statements artifact (S0-0.3).

13.3 North Star Metric

GuestIQ's North Star Metric is the percentage of respondents who complete their selected tier, measured as complete sessions ÷ started sessions for the same property_id, at the close of the pilot window.

Measurement: SELECT COUNT(*) WHERE is_complete = true / COUNT(*) WHERE property_id = 'PROP001', via Supabase SQL Editor or management dashboard. Thresholds: ≥80% Stretch, ≥60% Pass (minimum — this IS the pilot completion rate success criterion), 40–59% At Risk, <40% Fail.

ℹ  The OKRs in Section 4 (success criteria) are the time-bound key results that operationalise this persistent goal. They are not renamed — they are identified as the operational implementation of the North Star. Full NSM specification including input metrics is in the NSM artifact (S0-0.5).

13.4 Scrum Master Function

GuestIQ has one human covering all human roles simultaneously. This creates a structural tension between Product Owner instincts (deliver) and Scrum Master instincts (protect process). The resolution: Claude holds the Scrum Master function at the start of each sprint session, running a 7-item checklist before any delivery work begins.

| Role | Scrum Master — held by Claude (AI Developer) at sprint start |
| --- | --- |
| Activation | First message of each sprint session that is explicitly a sprint start |
| Duration | 5 minutes maximum — 7-item checklist only |
| Checklist items | (1) Previous gate conditions confirmed · (2) Epic/Feature/Story hierarchy correct · (3) DoR satisfied for all entering stories · (4) TDD test specifications in place · (5) PLG metric check (Sprints 5–6) · (6) Methodology impediments · (7) Use Case model current |
| Authority | Can and must flag any unmet condition before delivery begins |

13.5 Work Hierarchy — Epic → Feature → Story → Task

All backlog items are organised in a four-level hierarchy derived from Use Case 3.0 applied to Scrum delivery.

| Level | Maps To | GuestIQ Definition |
| --- | --- | --- |
| EPIC | = Use Case | Complete user journey. Contains all scenarios and extensions. Spans multiple sprints. Owner: SH-02 (research) / SH-04 (technical). |
| FEATURE | = Use Case Slice | Staged, implementable path through a Use Case. Bounded to one sprint. Includes requirements + design + code + tests (TDD Principle 10). |
| USER STORY | = Work Item | Sprint-sized deliverable. Acceptance criteria = the test specification (BDD). Satisfies DoR before sprint. Satisfies DoD before marking done. |
| TASK | = Implementation Detail | Sub-day item. Internal to the session. Not tracked in formal backlog. Optional for simple stories. |

13.6 Framework Interaction Priority

When two frameworks give different guidance on the same issue, the following priority order governs. Earlier rules always take precedence.

| 1 — Academic research integrity | Unconditional. If research data is compromised, the pilot pauses — regardless of schedule, delivery pressure, or any other framework. |
| --- | --- |
| 2 — Scrum Master process | SM checklist runs before delivery. Any failure blocks new work until resolved. |
| 3 — TDD test specification | Test spec precedes code, always. 84-path matrix before Sprint 2. Playwright before post-Sprint 4 deployments. |
| 4 — PRINCE2 governance artifacts | Governance artifacts updated before new story work begins. Risk Register at sprint start. |
| 5 — PLG engagement design | Serves user adoption within constraints set by priorities 1–4. |
| 6 — JTBD user goals | Goals define what to build; constraints define how. A goal is never dropped — a feasible alternative is found. |

# 12. PROJECT AUTHORIZATION AND APPROVAL

★ UPDATED v2.0:  Re-approval required in v2.1: Section 13 (Delivery Methodology) added. Risk count corrected from 10 to 12. Version 2.0 approval is noted and remains on record. All v2.1 changes are additive — no previously approved content has been removed or contradicted.

By signing below, each stakeholder confirms they have read and understood this Project Charter v2.0, agree that it accurately and completely represents the project purpose, scope, objectives, and success criteria as updated from v1.0, and authorize the project to proceed to Sprint 1 on the basis of this updated charter.

| Role | Name & Signature | Date Approved |
| --- | --- | --- |
| Project Sponsor / Hotel Management |  |  |
| Lead Researcher |  |  |
| Developer (AI Representative) |  |  |

| Version 1.0 approval | Approved by Lead Researcher prior to planning phase |
| --- | --- |
| Version 2.1 changes | Additive only — Section 13 added (Delivery Methodology). Risk count corrected. No content removed. |
| Re-approval requirement | All signatories must re-approve v2.0 before Sprint 1 begins |
| Next version trigger | Material scope change, objective change, or timeline change during Sprints 1–6. All signatories must re-approve v2.1 before Sprint 1 begins. |

ℹ NOTE:  This Project Charter v2.0 supersedes v1.0 for all purposes from the date of v2.0 approval. Version 1.0 is retained on file for audit purposes. The Master Development Timeline, SRS, and all subsequent Sprint 0 artifacts reference this v2.0 Charter as the authoritative founding document.

— END OF PROJECT CHARTER v2.0 —

GuestIQ — Hotel Guest Expectations Research Application  ·  Project Charter v2.1  ·  Sprint 0 Artifact