RISK REGISTER

GuestIQ — Hotel Guest Expectations Research Application

Version 1.2 · S0-1.9 · v1.2 PENDING RE-APPROVAL

| Document ID | S0-1.9 — Sprint 0 Artifact (living document) |
| --- | --- |
| Document Version | 1.2 — R-13, R-14, R-15 added (Documentation Drift · Production-Deploy Gap · Mobile UI Bug Class). New category: Process. |
| Document Status | APPROVED v1.1 — v1.2 PENDING RE-APPROVAL |
| Project | GuestIQ — Hotel Guest Expectations Research Application |
| Sprint | Sprint 0 — Foundation & Governance (updated at Sprint 4 planning) |
| Prepared By | Claude (AI Developer) |
| Date Prepared | 31 May 2026 |
| Total Risks | 15 risks across 8 categories |
| Risk Distribution | High: 5 · Medium: 7 · Low: 3 · Critical: 0 |
| Changes from v1.1 | R-13 added: Documentation Drift across SRS / Product Backlog / Sprint Backlog (Medium/Medium). R-14 added: Production-Deploy Gap (High/High) — the only new High risk. R-15 added: Mobile-Specific UI Bug Class Invisible in DevTools (Medium/Medium). New category added: Process (Quality + Delivery). All three risks surfaced in the Sprint 3 Retrospective. Heatmap, summary table, and distribution updated. No existing risk content changed. |
| Next Mandatory Update | Start of Sprint 4 — and at the start of every subsequent sprint |
| Related Documents | Project Charter v2.1 (S0-1.1v) · Methodology Document v1.1 (S0-0.1) · Stakeholder Register v1.1 (S0-1.3v) · Sprint 3 Retrospective (S3 close) · Definition of Done + Ready v1.2 (S0-1.7) |
| Document Location | 04-Sprint-4 / AI-Outputs / Risk-Register-v1.2.docx |

ℹ  This is a living document. Reviewed and updated at the start of every sprint. New risks are added as identified. Resolved risks are marked Closed — never deleted. The Lead Researcher is the risk register owner.

# 1. PURPOSE AND SCOPE

The Risk Register is the central repository for all identified project risks. A risk is an uncertain event that, if it occurs, will have a negative effect on the project’s ability to achieve its objectives. This register documents only negative risks — threats to schedule, quality, data integrity, or stakeholder satisfaction.

Each risk is assessed for probability (how likely it is to occur) and impact (how severe the consequences would be if it does occur). These two dimensions combine to determine the overall risk level — which drives the urgency and depth of mitigation.

Version 1.1 added two new risks identified during the Sprint 0 methodology discussion: R-11 (the single human covering all human roles — the highest structural risk in the project) and R-12 (mid-project methodology adoption — the risk that introducing Use Case 3.0 and the Epic hierarchy mid-project creates confusion). A new category, Methodology, was added to house these risks.

Version 1.2 adds three risks identified during the Sprint 3 Retrospective: R-13 (documentation drift across the SRS, Product Backlog, and Sprint Backlog), R-14 (the production-deploy gap, where locally verified work is treated as Done before it is deployed and verified on the live URL — the only new High risk), and R-15 (a class of mobile UI bugs visible only on the real target device and not in DevTools emulation). A new category, Process, is added to house R-13 and R-14; R-15 joins the existing Technical category.

ℹ  Risks that are not documented are not managed. If you identify a new risk at any point during the project, add it to this register immediately — do not wait for the next sprint review.

# 2. RISK SCORING METHODOLOGY

## 2.1 Probability

| Level | Definition | Example |
| --- | --- | --- |
| High | More likely than not to occur — probability > 60% | Decision latency — hotel operations regularly interrupt review time |
| Medium | May or may not occur — probability 30–60% | Branching logic error — careful review reduces but cannot eliminate |
| Low | Unlikely to occur — probability < 30% | Supabase outage — rare for established platform on free tier |

## 2.2 Impact

| Level | Definition | Example |
| --- | --- | --- |
| High | Threatens project completion, data integrity, or pilot success criteria | Corrupted research data — invalidates the core project deliverable |
| Medium | Delays a sprint or reduces quality of a specific deliverable | A feature works incorrectly — requires rework but does not corrupt data |
| Low | Minor inconvenience with no lasting effect on project outcomes | A visual display issue on one screen — fixed in the next deployment |

## 2.3 Risk Level Matrix

Probability and Impact combine to determine the overall Risk Level. This determines the urgency and depth of mitigation required.

| Impact ↓ / Probability → | Low Probability | Medium Probability | High Probability |
| --- | --- | --- | --- |
| High Impact | Medium | High | High |
| Medium Impact | Low | Medium | High |
| Low Impact | Low | Low | Medium |

# 3. RISK SUMMARY AND HEATMAP

## 3.1 Risk Summary Table — All 15 Risks

All 15 identified risks listed in order of risk level. Use this table for rapid reference. Full risk cards with triggers, mitigation, and contingency plans are in Section 4.

| ID | Risk Title | Prob. | Impact | Level | Primary Mitigation |
| --- | --- | --- | --- | --- | --- |
| R-01 | Decision Latency | High | High | HIGH | Dedicated calendar blocks. 48h commitment. AI follows up at 36h. |
| R-02 | Branching Logic Errors | Medium | High | HIGH | 84-path test matrix in Sprint 1. Every path tested in Sprint 3. |
| R-03 | Low Front Desk Pilot Participation | Medium | High | HIGH | Identity labels. Management endorsement. Day 5 follow-up. Results screen reward. |
| R-11 | Single Human Covering All Human Roles | High | High | HIGH | Scrum Master function held by Claude. SM checklist enforces process discipline separate from delivery pressure. |
| R-14 | Production-Deploy Gap | High | High | HIGH | DoD v1.2: deploy to live URL AND Lead Researcher production verification as explicit closing gate. |
| R-04 | Browser Incompatibility on Front Desk PCs | Low | High | MEDIUM | Test on every front desk PC in Sprint 4. Chrome available as fallback. |
| R-05 | JSON Configuration File Corruption | Medium | Medium | MEDIUM | Config validator on every load. Git version control. JSON linter before deploy. |
| R-06 | Supabase Project Accidental Deletion | Low | High | MEDIUM | Weekly CSV to OneDrive. Email confirmation gate. Supabase support as fallback. |
| R-08 | Scope Creep During Build Sprints | Medium | Medium | MEDIUM | Formal change request required. Phase 2 backlog captures good ideas without disrupting Phase 1. |
| R-12 | Mid-Project Methodology Adoption | Medium | Medium | MEDIUM | Methodology Document produced first as anchor. Phased adoption. Sprint 1 gate confirms adoption is stable. |
| R-13 | Documentation Drift (SRS / Product Backlog / Sprint Backlog) | Medium | Medium | MEDIUM | SRS authoritative. Sprint Backlog references FR IDs rather than restating acceptance criteria. |
| R-15 | Mobile UI Bug Class Invisible in DevTools | Medium | Medium | MEDIUM | First diagnostic evidence on real target device. Stop coding after two failed fix attempts. |
| R-07 | Supabase Service Outage During Pilot | Low | Medium | LOW | Offline queue. Downtime screen. Sentry monitoring. Retry every 30 seconds. |
| R-09 | Gamification Disengagement | Low | Medium | LOW | Professional framing first. UAT specifically probes gamification. Can disable if needed. |
| R-10 | PostHog or Sentry Data Privacy Concern | Low | Low | LOW | IP anonymization. No PII. Privacy notice on welcome screen. Session replay disableable. |

## 3.2 Risk Heatmap

Each risk is plotted by probability and impact. Risk IDs in the red zone require active mitigation. Risk IDs in the amber zone require monitoring. Risk IDs in the green zone require awareness. All 15 risks are plotted.

| Impact ↓ Prob → | Low | Medium | High | Risk Level |
| --- | --- | --- | --- | --- |
| High Impact | R-04 R-06 R-11 | R-02 R-03 R-12 | R-01 R-14 | High |
| Medium Impact | R-07 R-09 | R-05 R-08 R-13 R-15 | — | Medium |
| Low Impact | R-10 | — | — | Low |

# 4. RISK REGISTER — FULL DETAIL

## HIGH RISKS — Require active mitigation now

### R-01  HIGH  Decision Latency

Category: Governance  |  Owner: SH-02 Lead Researcher  |  Status: ACTIVE

| Artifact reviews by the Lead Researcher take longer than 48 hours, delaying sprint starts. Since all AI deliverables require human review before the next step begins, any review delay cascades directly into sprint timeline slippage. |  | Probability High |  | Impact High | Level HIGH |
| --- | --- | --- | --- | --- | --- |
| Warning Signs / Triggers Review not complete within 24 hours of delivery. Researcher unavailable due to operational demands at the property. Multiple artifacts delivered simultaneously creating a review backlog. | Mitigation Strategy Lead Researcher blocks dedicated review time in calendar at sprint start and end. 48-hour turnaround is a formal project commitment documented in the Stakeholder Register. AI Developer follows up if no response within 36 hours. Only one artifact delivered for review at a time — never a batch of documents simultaneously. |  | Contingency If Risk Occurs If review exceeds 72 hours: sprint timeline is extended by the delay duration. The Master Development Timeline is updated. No work begins on the next step until the delayed review is complete. Sprint gate cannot be passed until all reviews for that sprint are confirmed. |  |  |

Review at: Reviewed at every sprint gate — the highest-priority process risk in the project

### R-02  HIGH  Branching Logic Errors

Category: Technical — Architecture  |  Owner: SH-02 + SH-04  |  Status: ACTIVE

| Errors in the Branching Logic Specification cause incorrect Module 5 routing — respondents are shown the wrong sub-section based on their Q1 answer. If undiscovered until the pilot, this corrupts research data for all affected sessions. |  | Probability Medium |  | Impact High | Level HIGH |
| --- | --- | --- | --- | --- | --- |
| Warning Signs / Triggers Specification reviewed under time pressure without systematic path checking. 84-path test matrix not completed before Sprint 2 begins. Module 5 testing skipped or abbreviated during Sprint 3. | Mitigation Strategy 84-path branching test matrix produced in Sprint 1 as an integrated part of the Branching Logic Specification. Sprint 1 gate explicitly requires this matrix to be approved before Sprint 2 coding begins. Every routing path tested individually during Sprint 3. AI implements strictly against the approved spec — any deviation flagged immediately. |  | Contingency If Risk Occurs If routing errors found during Sprint 3 testing: fix immediately and re-test all affected paths before proceeding. If errors found during the pilot: suspend the pilot, fix within 24 hours, invalidate affected sessions, notify respondents, restart their sessions from the beginning. |  |  |

Review at: Sprint 1 gate (matrix approval) + Sprint 3 (systematic path testing)

### R-03  HIGH  Low Front Desk Pilot Participation

Category: Participation  |  Owner: SH-02 Lead Researcher  |  Status: ACTIVE

| Fewer than 70% of the front desk team (fewer than 7 of 10 members) start the questionnaire during the 2-week pilot window, producing a dataset too small for meaningful operational insights. |  | Probability Medium |  | Impact High | Level HIGH |
| --- | --- | --- | --- | --- | --- |
| Warning Signs / Triggers Pilot launched during an unusually busy period. Team unaware of or confused by the Teams launch message. Questionnaire feels too long or irrelevant. No visible management endorsement. | Mitigation Strategy Identity-based tier labels motivate participation. Hotel Management visibly endorses without mandating. Launch message sent at start of a shift. Day 5 follow-up message and in-person check-in if fewer than 3 members have started. Bug Reporting Guide pinned to Teams. Results screen provides immediate visible reward — respondents see their own data compared to the team aggregate. |  | Contingency If Risk Occurs If fewer than 5 members started by Day 7: extend pilot by 1 week. Send personal (not group) messages to non-participants. Request hotel manager to mention the pilot in team briefing. If participation remains below 50% after extension: document the barrier as a research finding and adjust success criteria in the debrief report. |  |  |

Review at: Sprint 5 (launch) + Sprint 6 (daily monitoring — every working day)

### R-11  HIGH  Single Human Covering All Human Roles  ★ NEW v1.1

Category: Methodology — Governance  |  Owner: SH-02 Lead Researcher (as risk owner) · SH-04 Claude (as mitigation holder)  |  Status: ACTIVE

| One person — the Lead Researcher — covers all human roles simultaneously: Project Sponsor liaison, Lead Researcher, UAT Facilitator, Pilot Monitor, and Hotel Management Liaison. This creates a structural tension between Product Owner instincts (deliver value, ship the feature) and Scrum Master instincts (protect process, enforce gates). Under time pressure, the delivery instinct consistently overrides the process instinct, leading to skipped DoR checks, premature gate declarations, and accumulated quality debt across sprints. |  | Probability High |  | Impact High | Level HIGH |
| --- | --- | --- | --- | --- | --- |
| Warning Signs / Triggers Sprint gate passed without all artifacts fully reviewed. DoR criteria skipped at sprint planning under time pressure. A story marked Done before all DoD criteria verified. Risk Register not updated at sprint start. Use Case model becoming stale without triggering a SM flag. | Mitigation Strategy Scrum Master function held by Claude (SH-04) at the start of each sprint session. Claude runs the 7-item SM checklist before any delivery work begins — separating the process guardian role from the delivery partner role structurally. The SM checklist is the formal mitigation: it gives process discipline a fixed, non-negotiable moment that precedes every sprint. Epic/Feature/Story hierarchy correctness is checked at SM level, not left to the Lead Researcher’s judgment under pressure. |  | Contingency If Risk Occurs If a gate is passed without full verification: the SM checklist flags the incomplete item immediately at the next sprint start. No new sprint stories begin until the gap is resolved. If the SM checklist itself is being skipped: this is a second-order instance of R-11 — escalate to the Lead Researcher as a project governance failure requiring immediate correction. Add the recurrence to the retrospective. |  |  |

Review at: Every sprint start — SM-CHECK step is the mitigation activation mechanism. Reviewed at every retrospective.

### R-14  HIGH  Production-Deploy Gap  ★ NEW v1.2

Category: Process — Delivery  |  Owner: SH-04 AI Developer (as delivery driver) · SH-02 Lead Researcher (as production-verification gate)  |  Status: ACTIVE

| Work that is code-complete and verified in the local environment is treated as Done before it is deployed to the live GitHub Pages URL and verified there. The Definition of Done can let “code merged and locally verified” feel like completion. In Sprint 3, three weeks of fixes (B-3-001, B-3-002, B-3-003) sat in the local working tree — locally verified but never pushed — and the gap was discovered only during mobile testing on the production URL in S3-15. Undeployed fixes mean the live application respondents actually use does not contain the work believed to be Done, silently invalidating sprint progress. |  | Probability High |  | Impact High | Level HIGH |
| --- | --- | --- | --- | --- | --- |
| Warning Signs / Triggers A fix is described as Done with no corresponding git push. git status shows committed work that is not on the deployed branch. A bug believed fixed still reproduces on the live URL. Verification is performed only in local development, never on guestiq.github.io. Several fixes accumulate locally between deploys. | Mitigation Strategy Definition of Done v1.2 rewords the production-verification criterion so that deployment to the live GitHub Pages URL AND verification there by the Lead Researcher — not by the developer in local development — is the explicit closing gate. “Ship to production” is an explicit step on every fix, never an assumption. PWA service-worker caching means verification uses a hard refresh or Private/Incognito window, since a standard refresh can serve stale cached JS. |  | Contingency If Risk Occurs If undeployed work is discovered: deploy immediately as a single clearly-described commit, then re-verify every affected behaviour on the live URL before declaring Done. If a sprint gate was passed with undeployed work: the gate is reopened until production verification is complete — no next-sprint stories begin until the gap is closed (consistent with the binary sprint-gate principle). |  |  |

Review at: Every sprint gate (production-verification confirmation) + every retrospective.

## MEDIUM RISKS — Monitor actively; mitigations in place

### R-04  MEDIUM  Browser Incompatibility on Front Desk PCs

Category: Technical — Infrastructure  |  Owner: SH-02 Lead Researcher  |  Status: ACTIVE

| The front desk PCs run a browser version or configuration not supported by the React PWA — the application fails to load or displays incorrectly. Internet Explorer (not supported) may be installed as the default on older Windows configurations. |  | Probability Low |  | Impact High | Level MEDIUM |
| --- | --- | --- | --- | --- | --- |
| Warning Signs / Triggers Front desk PCs not verified before pilot launch. A PC runs Internet Explorer as default. A recent browser auto-update introduces a breaking change. A security policy blocks JavaScript execution. | Mitigation Strategy Lead Researcher verifies the application on each of the 3 front desk PCs during Sprint 4 testing — specifically opening the GitHub Pages URL, completing the Amateur flow, and verifying session data in Supabase. Edge and Chrome are pre-installed on all Windows 10/11 machines. This test is a Sprint 4 gate condition. |  | Contingency If Risk Occurs If a PC runs only Internet Explorer: install Chrome (requires no IT involvement — Chrome installer runs with standard user privileges on Windows 10/11). If a security policy blocks JavaScript: exclude that PC and use remaining PCs. If all PCs are blocked: escalate to IT with a specific whitelist request for guestiq.github.io. |  |  |

Review at: Sprint 4 (front desk PC verification test) + Sprint 5 (pre-launch check on all 3 PCs)

### R-05  MEDIUM  JSON Configuration File Corruption

Category: Technical — Content  |  Owner: SH-04 AI Developer  |  Status: ACTIVE

| A malformed JSON configuration file causes the application to fail on load after the Phase 1b content extraction. Respondents encounter a blank or broken screen instead of the questionnaire. |  | Probability Medium |  | Impact Medium | Level MEDIUM |
| --- | --- | --- | --- | --- | --- |
| Warning Signs / Triggers Phase 1b JSON extraction introduces a syntax error. A subsequent content edit introduces a formatting error. A file is saved with incorrect encoding. | Mitigation Strategy Configuration validator active from Phase 1b onwards: all 6 JSON files parsed and validated on every application load before any content renders. Malformed files produce a clear error, not a blank screen. All JSON files version-controlled in Git — instant rollback available. AI Developer runs JSON linter before every deployment. |  | Contingency If Risk Occurs If malformed JSON found during pilot: revert to last committed version via Git (single command). Redeploy via GitHub Actions (2-minute process). Notify affected team members via Teams. The validator error message identifies the specific malformed file — diagnosis is near-instant. |  |  |

Review at: Sprint 3 (Phase 1b extraction and validation testing) + ongoing

### R-06  MEDIUM  Supabase Project Accidental Deletion

Category: Data  |  Owner: SH-02 Lead Researcher  |  Status: ACTIVE

| The Supabase project containing all pilot research data is accidentally deleted. Free-tier projects can be deleted with a single click and email confirmation — there is no billing friction or grace period on free tier. |  | Probability Low |  | Impact High | Level MEDIUM |
| --- | --- | --- | --- | --- | --- |
| Warning Signs / Triggers Researcher navigates to the Supabase dashboard settings while fatigued. An accidental delete confirmation email is clicked. A team member with shared credentials deletes the project thinking they are working on a test environment. | Mitigation Strategy Weekly CSV export to OneDrive starting Sprint 6 Day 1 — two weeks of backups before pilot ends. Supabase project deletion requires email confirmation — the confirmation email is a second safety gate. Only the Lead Researcher has Supabase credentials. Supabase free tier projects can be restored within 7 days via support request. |  | Contingency If Risk Occurs If the project is deleted: immediately contact Supabase support for restoration. The most recent weekly CSV backup provides a fallback dataset. If restoration fails: the CSV backup is the research dataset — Supabase is reconstructed from the backup. Document the incident and the backup recovery process in the debrief report. |  |  |

Review at: Sprint 6 (daily monitoring checklist includes Supabase project status verification)

### R-08  MEDIUM  Scope Creep During Build Sprints

Category: Scope  |  Owner: SH-01 Hotel Management (as requester) · SH-02 Lead Researcher (as decision maker)  |  Status: ACTIVE

| New features or modifications are requested during Sprints 2–4 that were not in the approved Product Backlog, diverting development time from the committed sprint deliverables and threatening the 14-week timeline. |  | Probability Medium |  | Impact Medium | Level MEDIUM |
| --- | --- | --- | --- | --- | --- |
| Warning Signs / Triggers Hotel Management requests an additional dashboard panel after seeing Sprint 2 results. A front desk team member suggests a new question during UAT. A new academic reference suggests a different taxonomy structure. | Mitigation Strategy All scope changes require a formal Scope Change Request as defined in the Project Charter. The change request is assessed for timeline and cost impact before any work begins. The Phase 2 backlog captures good ideas without disrupting Phase 1 — any new feature request is immediately evaluated: Phase 1 or Phase 2? Changes after Sprint 2 has begun carry a high risk of timeline extension and are presumed Phase 2 unless the Lead Researcher explicitly justifies Phase 1 inclusion. |  | Contingency If Risk Occurs If a scope change is approved after Sprint 2: the timeline is formally extended and the Master Development Timeline updated. Deprioritize a lower-priority backlog item to compensate. Document the change and its timeline impact in the Version Update Log. If scope change is not approved: document the request in the Phase 2 Recommendations Document for future consideration. |  |  |

Review at: Sprint gate reviews — check for unapproved changes at every sprint review

### R-12  MEDIUM  Mid-Project Methodology Adoption  ★ NEW v1.1

Category: Methodology  |  Owner: SH-02 Lead Researcher (as risk owner) · SH-04 Claude (as adoption driver)  |  Status: ACTIVE

| Introducing Use Case 3.0, the Epic→Feature→Story→Task hierarchy, and the Scrum Master function mid-project — after the Product Backlog, RACI, and DoD+DoR were already produced — creates confusion about where artifacts belong, how Stories relate to Epics, and what the Scrum Master role does in practice. The risk is adoption overhead that slows delivery during Sprints 1–2 as the team adjusts to the new methodology layer. |  | Probability Medium |  | Impact Medium | Level MEDIUM |
| --- | --- | --- | --- | --- | --- |
| Warning Signs / Triggers Sprint 1 planning session produces stories without Epic/Feature parents. The Scrum Master checklist adds overhead that feels bureaucratic rather than useful. Use Case 3.0 slicing creates scope discussions that extend Sprint planning beyond the allocated time. The Lead Researcher expresses uncertainty about when to consult Use Cases vs. backlog. | Mitigation Strategy GuestIQ Methodology Document v1.1 (S0-0.1) is the anchor artifact — all framework decisions documented before adoption begins. Phased adoption: Use Case 3.0 applied at Sprint 0 Use Case Specifications (S0-2.5) level only — backlog restructuring is additive. Epic hierarchy added to Backlog v1.1 as a grouping layer — existing stories unchanged. SM checklist is 5 minutes maximum and lightweight by design. Sprint 1 gate explicitly confirms adoption is stable before Sprint 2 begins. |  | Contingency If Risk Occurs If Epic hierarchy causes confusion in Sprint 1 planning: defer Epic grouping to Sprint 1 retrospective and treat the backlog as flat for Sprint 1 only. Document the deferral. If SM checklist creates friction: reduce to 3 items (gate conditions, DoR, impediments) for Sprint 1 only, then restore full 7 items from Sprint 2. If Use Case model becomes a delivery bottleneck: treat Use Cases as reference documents only — stop updating them mid-sprint, defer updates to sprint retrospective. |  |  |

Review at: Sprint 1 gate (first post-adoption sprint — methodology stability confirmed) + Sprint 1 retrospective

### R-13  MEDIUM  Documentation Drift Across SRS / Product Backlog / Sprint Backlog  ★ NEW v1.2

Category: Process — Quality  |  Owner: SH-02 Lead Researcher (as risk owner) · SH-04 Claude (as documentation author)  |  Status: ACTIVE

| The same requirement is specified differently across the SRS, the Product Backlog, and the Sprint Backlog, so the three documents disagree about what a story actually requires. In Sprint 3, S3-14 (streak mechanic) carried three conflicting specifications — SRS FR-047 and Product Backlog v3.1 both described a multi-day mechanic, while Sprint Backlog v1.0 described a within-session mechanic. S3-16 had a parallel conflict — SRS FR-012 specified buttons while the Sprint Backlog specified dropdowns, and the Sprint Backlog cited the wrong FR cross-references (FR-065–067, which govern the dashboard). When documents drift, the team builds against the wrong specification and discovers the conflict only at review — or after deployment. |  | Probability Medium |  | Impact Medium | Level MEDIUM |
| --- | --- | --- | --- | --- | --- |
| Warning Signs / Triggers A Sprint Backlog story restates acceptance-criteria text rather than referencing the SRS FR ID. The same feature is described with different mechanics in two documents. A story cites an FR ID that, on inspection, governs an unrelated feature. A “which spec is right?” question arises during sprint planning or review. | Mitigation Strategy The SRS is designated the single authoritative source for functional requirements. Sprint Backlog stories reference the governing FR by ID and cross-link to the SRS rather than restating its acceptance-criteria text (DoD/DoR v1.2 amendment). When a conflict is found, the SRS wins and the drifted document is corrected — never the SRS. Retired requirements (FR-047, FR-012, FR-014, FR-097, FR-098) are removed from the SRS and any parallel documents in the same cleanup so stale specs cannot be built against. |  | Contingency If Risk Occurs If drift is found during planning: stop, reconcile against the SRS before the story enters the sprint, and log the correction in the affected document’s version log. If drift is found after a story is built (as in Sprint 3): apply the value-justification test to decide whether to fix-forward or drop the story, and record the decision in the retrospective. |  |  |

Review at: Every sprint planning (DoR check) + every sprint retrospective

### R-15  MEDIUM  Mobile-Specific UI Bug Class Invisible in DevTools  ★ NEW v1.2

Category: Technical — Quality  |  Owner: SH-04 AI Developer (diagnosis) · SH-02 Lead Researcher (target-device evidence)  |  Status: ACTIVE

| A class of UI defects appears only on the real mobile target device (iOS Safari / WebKit) and does not reproduce in Chrome DevTools mobile emulation, which runs the Blink engine. Diagnosing such bugs from source code or desktop emulation leads to plausible-but-wrong root causes and wasted fix cycles. In Sprint 3, B-3-005 (badge toast overflowing the screen edge on iOS Safari) took four iterations: two deploy cycles were burned on wrong diagnoses (transformed-ancestor reparenting; Framer Motion transform override) before real DOM evidence from the device revealed a WebKit-specific interaction between position: fixed, transform: translateX(-50%), and concurrent Framer Motion transforms. |  | Probability Medium |  | Impact Medium | Level MEDIUM |
| --- | --- | --- | --- | --- | --- |
| Warning Signs / Triggers A bug reproduces on a phone but not in Chrome DevTools mobile view. Two fix attempts do not move the needle. A CSS bug is diagnosed by pattern-matching to a familiar-sounding cause without runtime evidence. Fixes target position: fixed + transform centring on toast-style components. The defect involves the iOS notch / Dynamic Island safe-area. | Mitigation Strategy For any mobile bug report, the first diagnostic evidence is captured on the real target device (DOM inspection, screenshots), not inferred from source or desktop emulation. Chrome DevTools mobile emulation is treated as insufficient for WebKit-specific bugs. When two fix attempts fail to move the needle, coding stops and real DOM evidence is gathered before the next attempt. For fixed-position centring on iOS, avoid transform: translateX(-50%); use left: 0; right: 0; margin: 0 auto and anchor with env(safe-area-inset-*). |  | Contingency If Risk Occurs If a mobile bug resists two fixes: halt, request target-device DOM evidence from the Lead Researcher, and re-diagnose from that evidence before further code changes. Record the wrong diagnoses in the bug log so they are not repeated. Add Android Chrome coverage where a defect may be platform-specific. |  |  |

Review at: Sprint 4 (Android Chrome coverage) + Sprint 5 UAT on front desk hardware + whenever a mobile bug is reported

## LOW RISKS — Awareness maintained; monitor passively

### R-07  LOW  Supabase Service Outage During Pilot

Category: Technical — Infrastructure  |  Owner: SH-04 AI Developer (technical) · SH-02 Lead Researcher (communications)  |  Status: ACTIVE

| Supabase experiences a service outage during the 2-week pilot window, preventing response data from being written to the database. Respondents attempting to complete the questionnaire receive errors or lose their responses. |  | Probability Low |  | Impact Medium | Level LOW |
| --- | --- | --- | --- | --- | --- |
| Warning Signs / Triggers Supabase status page shows degraded performance. Response records are not appearing in the Supabase Table Editor despite sessions completing. Sentry raises errors related to Supabase API calls. | Mitigation Strategy Offline response queue implemented in Sprint 2: all responses stored in browser local storage when Supabase is unreachable, automatically retried every 30 seconds when connectivity is restored. Supabase downtime screen implemented in Sprint 4: if Supabase is completely unreachable, a friendly “temporarily unavailable” message is shown rather than a broken application. Sentry monitoring sends immediate alerts to Lead Researcher email. |  | Contingency If Risk Occurs If Supabase is down during the pilot: the offline queue preserves all response data in respondents’ browsers. Notify affected team members to leave their browser window open until connectivity is restored. If the outage exceeds 4 hours: extend the pilot window by 1 day to compensate. If responses are lost despite the queue (catastrophic failure): fall back to paper copies of the top-priority questions (Q1, Q5, Q7) and enter manually into Supabase. |  |  |

Review at: Sprint 2 (offline queue test) + Sprint 6 (daily monitoring)

### R-09  LOW  Gamification Disengagement

Category: Participation  |  Owner: SH-02 Lead Researcher  |  Status: ACTIVE

| The gamification mechanics feel forced, patronizing, or inconsistent with the professional identity of the front desk team — reducing engagement rather than increasing it. |  | Probability Low |  | Impact Medium | Level LOW |
| --- | --- | --- | --- | --- | --- |
| Warning Signs / Triggers UAT participants express discomfort with badge awards. Curiosity hook text feels generic. Tier upgrade prompt ignored by all UAT participants. Team refers to the tool as “a game” dismissively. | Mitigation Strategy Identity-based tier labels establish professional framing before any gamification appears. Episode map is a professional progress visualization — not a game board. Badges use research-appropriate names. UAT in Sprint 5 specifically probes gamification perception with direct feedback questions. Gamification is designed to be disableable — each mechanic is an independent component. |  | Contingency If Risk Occurs If UAT reveals gamification is actively harmful: remove badge reveal animations and reduce badge prominence. Keep progress bar and episode map (functional, not decorative). If tier upgrade prompt is the issue: disable upgrade prompts and set all respondents to Expert tier directly. Document in debrief report for Phase 2 redesign. |  |  |

Review at: Sprint 5 UAT (specific gamification feedback questions)

### R-10  LOW  PostHog or Sentry Data Privacy Concern

Category: Data  |  Owner: SH-02 Lead Researcher  |  Status: ACTIVE

| A front desk team member or hotel management raises a concern that observability tools (PostHog session replay, Sentry error logging) are collecting personal or sensitive data without appropriate consent. |  | Probability Low |  | Impact Low | Level LOW |
| --- | --- | --- | --- | --- | --- |
| Warning Signs / Triggers A team member asks what data is being collected. Hotel management receives a GDPR inquiry. A team member notices “session replay” in the PostHog dashboard and becomes concerned. | Mitigation Strategy Both platforms configured with IP anonymization enabled from Sprint 2 day one — no IP addresses collected. No PII collected at any point. Privacy notice on the welcome screen. Session replay captures mouse movements and click patterns only — no keystrokes, no personal data. Session IDs are anonymous UUIDs. |  | Contingency If Risk Occurs If a privacy concern is raised: provide a plain English explanation of what is and is not collected. Offer to disable session replay in PostHog (analytics events continue — minimal research impact). Demonstrate the PostHog and Sentry dashboards to show the actual data visible. If concern cannot be resolved: disable PostHog and Sentry entirely — research data in Supabase is unaffected. |  |  |

Review at: Sprint 5 (pilot launch welcome screen review) + Sprint 6 (as raised by team)

# 5. RISK REGISTER UPDATE PROCESS

The Risk Register is updated at the start of every sprint. The update process takes approximately 15 minutes and follows these steps:

| 1 | Review each open risk: has its probability or impact changed since the last sprint? If so, update the rating and note the change in the Version Update Log. |
| --- | --- |
| 2 | Check for new risks: have any events occurred in the last sprint that suggest risks not currently on the register? If so, add a new risk card immediately. |
| 3 | Mark resolved risks as Closed: if a risk’s trigger window has passed (e.g. R-04 browser incompatibility after Sprint 4 PC verification), mark it Closed. Do not delete it. |
| 4 | Update sprint review dates: change the “Review at” field on each card to reflect when it will next be reviewed. |
| 5 | Version the document: increment the version number, add a row to the Version Update Log, and file the new version in the sprint’s AI-Outputs folder. |

# 6. VERSION UPDATE LOG

| Version | Sprint | Updated By | Change Description |
| --- | --- | --- | --- |
| v1.0 | Sprint 0 | Claude / AI Developer | Initial version. 10 risks identified across 6 categories. Risk heatmap, summary table, full risk cards, and scoring methodology established. |
| v1.1 | Sprint 0 | Claude / AI Developer | Two new risks added: R-11 Single Human Covering All Human Roles (High/High/High) — mitigated by the Scrum Master function held by Claude. R-12 Mid-Project Methodology Adoption (Medium/Medium/Medium) — mitigated by the Methodology Document as anchor and phased adoption. New category added: Methodology. Total risks 10 → 12. Distribution: High 3→4, Medium 4→5. Heatmap and summary table updated. No existing risk content changed. |
| v1.2 | Sprint 4 (planning) | Claude / AI Developer | Three new risks added from the Sprint 3 Retrospective: R-13 Documentation Drift across SRS / Product Backlog / Sprint Backlog (Medium/Medium/Medium); R-14 Production-Deploy Gap (High/High/High) — the only new High risk, paired with the Definition of Done v1.2 production-verification amendment; R-15 Mobile-Specific UI Bug Class Invisible in DevTools (Medium/Medium/Medium). New category added: Process (Quality + Delivery). Total risks 12 → 15. Distribution: High 4→5, Medium 5→7. Heatmap, summary table, and distribution updated. No existing risk content changed. |

— END OF RISK REGISTER v1.2 —

GuestIQ · Risk Register v1.2 · S0-1.9 · Sprint 0 Artifact · Update at the start of every sprint